## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Data Team |  | Missing values in Azure Compute usage dataset causing inconsistent model inputs during data cleaning phase | Sprint 1 | Data Engineering Team
2 | Data Team |  | External economic indicators file format mismatch preventing merge with internal Azure usage data | Sprint 1 | Data Engineering Team
3 | QA Team |  | Regional dimension missing from Storage usage dataset resulting in incomplete geographic coverage | Sprint 1 | Data Engineering Team
4 | Data Team |  | Lag variable generation producing NaN values for early time-series rows causing downstream model failures | Sprint 2 | ML Engineering Team
5 | Data Team |  | Seasonality flag engineering applying incorrect fiscal quarter boundaries for Azure billing cycle | Sprint 2 | ML Engineering Team
6 | QA Team |  | Usage spike detection threshold too sensitive flagging normal weekend dips as anomalies | Sprint 2 | ML Engineering Team
7 | ML Team |  | ARIMA model training failing on non-stationary Azure Storage series without differencing step | Sprint 3 | ML Engineering Team
8 | ML Team |  | XGBoost model overfitting on training data with RMSE gap >40% between train and validation sets | Sprint 3 | ML Engineering Team
9 | QA Team |  | Backtesting module using future data leakage in rolling window calculation inflating accuracy metrics | Sprint 3 | ML Engineering Team
10 | ML Team |  | Model comparison report generating incorrect MAE values due to unit inconsistency (TB vs GB) | Sprint 3 | ML Engineering Team
11 | DevOps |  | Real-time forecasting pipeline experiencing 8-second response latency exceeding SLA threshold of 2 seconds | Sprint 4 | DevOps / ML Team
12 | QA Team |  | Capacity planning dashboard not reflecting updated forecast after model retraining event | Sprint 4 | Frontend / API Team
13 | DevOps |  | Automated reporting job failing silently on Azure Functions due to missing environment variable in production config | Sprint 4 | DevOps Team
14 | QA Team |  | Monitoring pipeline not triggering model retraining when forecast drift exceeds defined threshold | Sprint 4 | ML Engineering Team
15 | Stakeholder |  | Forecast-driven infrastructure recommendation engine suggesting over-provisioning in low-demand regions | Sprint 4 | ML Engineering Team

## Sheet2
Logical
User Interface
Maintainability
Standards
Others